## Backlogs
Product backlog |  |  |  |  | Sprint backlog
id | story | priority | time estimate | completed | id | story | responsible person | time estimate | completed (%) | completed before (%)
1 | Users can play the game as a multiplayer online game | 5 | 8 | 4 | 1 | Users can play the game as a multiplayer online game | Deniz | 8 | 75 | 50
2 | Users can interact with other players | 5 | 6 | 2.5 | 11 | Users can interact with the environment with realistic physics | Emre | 6 | 50 | 30
3 | Other users' moves will be able to seen | 5 | 4 | Not started | 2 | Users can interact with other players | Deniz | 6 | 80 | 40
4 | Users will be able to shoot other users | 5 | 4 | Not started | 6 | Users will see environmental objects (e.g. walls) | Erdi | 10 | 50 | 0
5 | Bullets will be effected by the environment objects | 2 | 4 | Not started | 7 | User movements will be shown with animations | Emre | 4 | 100 | 75
6 | Users will see environmental objects (e.g. walls) | 2 | 10 | Not started | 4 | Users will be able to shoot other users | Eren | 4 | 50 | 0
7 | User movements will be shown with animations | 2 | 4 | 3 | 12 | User will be able to shoot their gun | Eren | 6 | 50 | 0
8 | Killing users will be shown with animations | 1 | 4 | 2 | 10 | Users will start the game by navigating through a menu | Deniz | 4 | 100 | 0
9 | Who killed whom info will be shown on the screen | 3 | 4 | Not started
10 | Users will start the game by navigating through a menu | 3 | 4 | Not started
11 | Users can interact with the environment with realistic physics | 3 | 6 | 2 |  |  | Completed work (man*hour) |  | 20.6
12 | User will be able to shoot their gun | 3 | 6 | Not started
13 | Users will hear gun shots | 3 | 6 | Not started
14 | Users will hear when another user is wounded | 3 | 6 | Not started
15 | Other users will have different colors | 2 | 2 | Not started
16 | Users will see their rank on a score-board | 1 | 4 | Not started
17 | Users will be able to move in the environment | 4 | 4 | 4
18 | Users will be able to point their gun | 3 | 2 | Not started
|  | Total work | 88

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 88 |  | Sprint count | 4
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3
Original estimate |  |  | 30
3 |  |  | 19.9
Realized total average |  |  | 19.9 |  | Trend count | 4
Average last 8 |  |  | 19.9
Avg. worst 3 in last 8 |  |  | 19.9
Trend |  |  | 19.9
These hidden cells are used to draw the graph on this page. DO NOT DELETE!
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 2
Original estimate - Avg |  |  | 3
Original estimate - Max |  |  | 5 |  | Standard Dev. | 0.98995
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 48.2
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 3
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [8 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom |  | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 88 | 24 | 19.2 | 88 | 88 | 88 | 0 | 0 |  | 88 | 88.2333 | 88.2333 | 7.1054e-15 | 19.9 | 19.9 | 19.9
2 | 68.8 | 24 | 20.6 | 88 | 68.8 | 68.8 | 3.5527e-15 | 3.5527e-15 |  | 68.8 | 68.3333 | 68.3333 | 7.1054e-15 | 19.9 | 19.9 | 19.9
3 | 48.2 |  |  | 88 | 48.2 | 48.2 | 7.1054e-15 | 7.1054e-15 |  | 48.2 | 48.4333 | 48.4333 | 7.1054e-15 | 19.9 | 19.9 | 19.9
4 | 48.2 |  |  | 88 | [6 empty] | 28.5333 | 28.5333 | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
[5 empty] | 0 | #REF! | #REF! | 7.1054e-15 | 19.9 | 19.9 | 19.9
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate