## Sheet2
Product backlog |  |  |  |  | Sprint backlog
id | story | priority | time estimate | status | id | story | responsible person | time estimate | completed (%)
1 | Users can connect a server and play the game with other players | 5 | 16 | Not started | 1 | Users can connect a server and play the game with other players | Deniz | 16 | 20
2 | Users can interact with other players | 5 | 10 | Not started | 10 | Users will start the game by navigating through a menu | Erdi | 4 | 20
3 | Other users' moves will be able to seen | 5 | 4 | Not started | 11 | Users can interact with the environment with realistic physics | Emre | 6 | 20
4 | Users will be able to shoot other users | 5 | 4 | Not started | 2 | Users can interact with other players | Deniz | 10 | 10
5 | Bullets will be effected by the environment objects | 2 | 4 | Not started | 17 | Users will be able to move in the environment | Emre | 6 | 100
6 | Users will see environmental objects (e.g. walls) | 2 | 10 | Not started | 7 | User movements will be shown with animations | Erdi | 4 | 20
7 | User movements will be shown with animations | 2 | 4 | Not started | 8 | Killing users will be shown with animations | Eren | 4 | 20
8 | Killing users will be shown with animations | 1 | 4 | Not started
9 | Who killed whom info will be shown on the screen | 3 | 4 | Not started
10 | Users will start the game by navigating through a menu | 3 | 4 | Not started
11 | Users can interact with the environment with realistic physics | 3 | 6 | Not started
12 | User will be able to shoot their gun | 3 | 6 | Not started
13 | Users will hear gun shots | 3 | 6 | Not started
14 | Users will hear when another user is wounded | 3 | 6 | Not started
15 | Other users will have different colors | 2 | 2 | Not started
16 | Users will see their rank on a score-board | 1 | 4 | Not started
17 | Users will be able to move in the environment | 4 | 4 | Not started
18 | Users will be able to point their gun | 3 | 2 | Not started